**Quiz - Principles**

Question 1:

What is NOT a PRINCE2 Principle?

A) Continued business justification

B) Project manage by process

C) Manage by stages

D) Tailor to suit the project environment

Question 2:

What is NOT one of the four integrated elements of PRINCE2?

A) Principles

B) Products

C) Themes

D) Tailoring to the project environment

**Quiz - Continued Business Justification**

Question 1:

What principle is a prerequisite for effective risk management?

A) Continued business justification

B) Manage by exception

C) Focus on products

D) Tailor to suit the project environment

Question 2:

According to PRINCE2, a project must have \_\_\_\_\_\_\_\_ justification. What words would BEST fill in the blank?

A) Senior manager

B) Continued business

C) Consistent user

D) Business operational

**Quiz - Managing Product Delivery**

Question 1:

What is a specific objective of the Managing Product Delivery process?

A) The project management team is focused on delivery within the tolerances laid down

B) The Business Case is kept under review

C) Attention is focused on delivery of the stage‚Äôs products

D) Team Managers, team members and suppliers are clear as to what is to be produced and what is the expected effort, cost, or timescale

Question 2:

When are Work Package tolerances are agreed upon?

A) When accepting a Work Package

B) When approving a Stage Plan

C) When creating the Project Plan

D) When creating the Project Brief

**Quiz - Learn from Experience**

Question 1:

What PRINCE2 element is described as being the guiding obligations and good practices to determine whether the project is being managed appropriately?

A) Principles

B) Processes

C) Themes

D) Tailoring PRINCE2 to the project environment

Question 2:

What BEST describes the purpose of a Lessons Report?

A) It is used to understand the detailed nature, purpose, function and appearance of a product

B) It allows the corporate group responsible for any quality management system to refine, change and improve the standards

C) It provides useful information regarding product status

D) It keeps the Project Board and any other stakeholders informed of stage progress

**Quiz - Defined Roles and Responsibilities**

Question 1:

What supports the incorporation of the primary stakeholders into the project management team?

A) Continued business justification

B) Defined roles and responsibilities

C) Manage by stages

D) Learn from experience

Question 2:

In PRINCE2, a project has defined \_\_\_\_\_\_\_ for each project objective to establish limits of delegated authority. What word best fills in the blank?

A) Allowances

B) Tolerances

C) Roles

D) Deviations

**Quiz - Manage By Stages**

Question 1:

What principle of PRINCE2 supports planning only to a level of detail that is manageable and foreseeable?

A) Continued Business Justification

B) Manage by Exception

C) Focus on Products

D) Manage by Stages

Question 2:

Complete this statement: PRINCE2 recommends three \_\_\_\_\_\_\_\_\_\_to reflect the needs of the different levels of management involved in a project.

A) Levels of issue

B) Stakeholders

C) Levels of plans

D) Types of risk responses

**Quiz - Manage by Exception**

Question 1:

What situation does the "creation of an exception plan" usually follow?

A) A time or cost slippage occurring during a management stage

B) An Exception Report being submitted to the Project Board in the case of a management stage is forecasted to exceed its tolerance

C) A Stage Plan updated due to an urgent corrective action being taken by the Project Manager

D) A newly identified risk being captured and documented in the Risk Register

Question 2:

According to the principles of PRINCE2, what statement is FALSE?

A) A project should have a customer/supplier environment

B) A project should manage by exception

C) A project should focus on products

D) A project should be tailored to suit the project environment

**Quiz - Focus on Products**

Question 1:

Fill in the blank: A PRINCE2 project focuses on \_\_\_\_\_\_\_\_\_\_, in particular their quality requirements.

A) The definition and realization of benefits

B) The definition and delivery of products

C) Project management team roles and responsibilities

D) The outcomes expected from the using the outputs

Question 2:

What best describes a successful project in PRINCE2 that follows the principle of "Focus on Products"?

A) Output oriented

B) Activity oriented

C) Benefits oriented

D) Resource oriented

**Quiz - Tailor to the Environment**

Question 1:

What is NOT a PRINCE2 Principle?

A) Continued business justification

B) Project manage by process

C) Manage by stages

D) Tailor to suit the project environment

Question 2:

If you adapt PRINCE2 to your specific organization or project, where should any changes be documented?

A) Project Initiation Document

B) Change Approach

C) Risk Management Approach

D) Communication Strategy

**Quiz - Themes**

Question 1:

Which PRINCE2 element is an aspect of project management that must be addressed continually and in parallel throughout the project?

A) Principles

B) Processes

C) Themes

D) Tailoring PRINCE2 to the project environment

Question 2:

What is NOT an integrated element of PRINCE2?

A) Principles

B) Techniques

C) Themes

D) Tailoring PRINCE2 to the project environment

**Quiz - Business Case**

Question 1:

What statement best describes a dis-benefit?

A) A risk which occurs and subsequently impacts a stakeholder

B) An outcome perceived as negative by one or more stakeholders which may occur during the project

C) An outcome perceived as negative by one or more stakeholders which has actual consequences

D) Any one of the project‚Äôs issues which directly affects a stakeholder

Question 2:

What is the Business Case theme's purpose?

A) Establish mechanisms to monitor and compare actual achievements against those planned

B) Establish methods to judge whether the ongoing project is justified

C) Assess and control uncertain events or situations

D) Describe how, when and at what cost products can be delivered

**Quiz - Organization**

Question 1:

What project management team roles can NOT be shared?

A) Project Assurance

B) Executive

C) Senior User

D) Senior Supplier

Question 2:

What role is accountable to the corporate or program management for the project's success?

A) Project Board

B) Project Manager

C) Senior User

D) Change Authority

**Quiz - Quality**

Question 1:

What quality technique standard and/or procedure is applied during the project?

A) Quality Register

B) Quality Management Strategy

C) Project Product Description

D) Quality assurance

Question 2:

What is the purpose of quality planning?

A) Provide information from the undertaking of the quality methods

B) Maintain the quality and approval records stemming from the planned quality checks

C) To produce the Project Plan with resource information

D) Identify the means by which quality will be achieved and assessed

**Quiz - Plans**

Question 1:

What product is used to define a budget for responding to potential threats and opportunities?

A) Risk Management Strategy

B) Risk Register

C) Issue Register

D) Project Plan

Question 2:

What product does the Project Board use as a baseline against which to monitor the project progress on a stage by stage basis?

A) Stage Plan

B) Project Plan

C) Program Plan

D) Benefits Review Plan

**Quiz - Risk**

Question 1:

What theme is used to assess and control the uncertainty within a project?

A) Progress

B) Risk

C) Change

D) Plans

Question 2:

What step looks at the probability, impact and proximity of a risk?

A) Communicate

B) Assess (estimate)

C) Identify (context)

D) Plan

**Quiz - Change**

Question 1:

What BEST describes the purpose of Change theme?

A) Prevent change to anything agreed in the Project Initiation Documentation

B) Ensure any potential changes to baselined products are controlled

C) Ensure that the correct versions are delivered to the customer

D) Assess changes to only the specialist products

Question 2:

What BEST defines an outcome?

A) A measurable improvement perceived as positive by one or more stakeholder

B) Any one of the specialist products

C) An actual negative consequence of doing the project

D) The result of change, normally affecting real-world behavior or circumstances

**Quiz - Progress**

Question 1:

What theme provides the mechanisms to forecast a project's continued viability?

A) Risk

B) Progress

C) Plans

D) Business Case

Question 2:

What is the purpose of the Progress theme?

A) Identify, assess, and control uncertainty

B) To establish mechanisms to monitor and control what has happened against what had been planned

C) Facilitate communication and control by defining the means of delivering the products

D) Define and implement the means by which the project will create and verify products which are fit for purpose

**Quiz - Processes**

Question 1:

What integrated element is the structure of PRINCE2 made up of?

A) Principles, Themes, Processes, Tailoring to the project environment

B) Outputs, Outcomes, Benefits

C) Organization, Plans, Progress, Business Case, Risk, Quality, Change

D) Time, Cost, Quality, Scope, Benefit, Risk

Question 2:

What statement is TRUE concerning a PRINCE2 project?

A) PRINCE focuses on engaging with the business stakeholders only

B) PRINCE2 does not seek to engage with any stakeholders outside of the project environment

C) PRINCE2 is based on a customer/supplier environment

D) PRINCE2 assumes the supplier will specify the desired result and probably pay for the project

**Quiz - Starting Up a Project**

Question 1:

What is a specific objective of the Starting Up a Project process?

A) To establish how the project‚Äôs products will be delivered and at what cost

B) Ensure there is a common understanding of the benefits expected from the project

C) To ensure there is business justification for initiating the project

D) To approve the Plan for the next Stage

Question 2:

What is produced in the Starting Up a Project process to define the way the project is to be delivered after evaluating the various delivery methods?

A) Outline Business Case

B) Project approach

C) Project definition

D) Project Product Description

**Quiz - Directing a Project**

Question 1:

During which process would the Project Manager escalating an exception?

A) Directing a Project

B) Managing a Stage Boundary

C) Initiating a Project

D) Controlling a Stage

Question 2:

What process manages and reviews the plans for achieving the expected benefits?

A) Managing Product Delivery

B) Initiating a Project

C) Directing a Project

D) Starting up a Project

**Quiz - Initiating A Project**

Question 1:

What is the purpose of the Communication Management Strategy?

A) Ensuring the project team can use the required reporting tools

B) Producing reports for the Project Board

C) Defining the communication method between the Project Board and corporate or program management

D) Ensuring stakeholders are aware of their responsibilities

Question 2:

What process ensures that the post-project benefits are realized, managed, and reviewed?

A) Closing a Project

B) Initiating a Project

C) Directing a Project

D) Starting up a Project

**Quiz - Controlling a Stage**

Question 1:

What is a specific objective of the Controlling a Stage process?

A) Attention is focused on delivery of the stage‚Äôs products

B) Assure the Project Board that all products in the Stage Plan for the current stage have been completed and approved

C) Work on products allocated to the team is authorized and agreed

D) The various ways the project can be delivered are evaluated and a project approach selected

Question 2:

What process would a concern about the amount of stage tolerance remaining be recorded in the Issue Register?

A) Directing a Project

B) Managing a Stage Boundary

C) Managing Product Delivery

D) Controlling a Stage

**Quiz - Managing a Stage Boundary**

Question 1:

What occurs during the Managing a Stage Boundary process?

A) Periodic review of progress against the Stage Plan

B) Obtain approvals for all completed products

C) Escalation of Issue Reports created during the current stage

D) Review of the business justification for the project

Question 2:

What is an objective of the Managing a Stage Boundary process?

A) Request authorization to start the next stage

B) Ensure that all threats and opportunities for the current stage have been closed

C) Make certain that work on products allocated to the team for the next stage is authorized and agreed

D) Implement actions to resolve tolerance deviations from the Stage Plan

**Quiz - Closing a Project**

Question 1:

Fill in the blank: The purpose of the Closing a Project process is to provide a fixed point at which acceptance for the \_\_\_\_\_\_\_\_\_\_ is confirmed.

A) Final project cost

B) Project product

C) Project scope

D) Project mandate

Question 2:

When is it determined if a project has met or achieved its objectives?

A) During the Closing a Project process

B) During the final end stage assessment

C) During the Controlling a Stage process

D) During the Managing Product Delivery process

**ANSWER KEY**

|  |  |
| --- | --- |
| Quiz: Principles  1. B  2. B  Quiz: Continued Business Justification  1. A  2. B  Quiz: Managing Product Delivery  1. D  2. A  Quiz: Learn from Experience  1. A  2. B  Quiz: Defined Roles and Responsibilities  1. B  2. B  Quiz: Manage by Stages  1. D  2. C  Quiz: Manage by Exception  1. B  2. A  Quiz: Focus on Products  1. B  2. A  Quiz: Tailor to the Environment  1. B  2. A | Quiz: Themes  1. C  2. B  Quiz: Business Case  1. B  2. B  Quiz: Organization  1. B  2. A  Quiz: Quality  1. B  2. D  Quiz: Plans  1. A  2. B  Quiz: Risk  1. B  2. B  Quiz: Change  1. B  2. D  Quiz: Progress  1. B  2. B  Quiz: Processes  1. A  2. C |

**Answer Key**

|  |  |
| --- | --- |
| Quiz: Starting Up a Project  1. C  2. B  Quiz: Directing a Project  1. A  2. C  Quiz: Initiating A Project  1. C  2. C  Quiz: Controlling a Stage  1. A  2. D  Quiz: Managing a Stage Boundary  1. D  2. A  Quiz: Closing a Project  1. B  2. A |  |